## Template 1 STOP Monthly Report
BAS Template 1 - STOP Monthly Report
Contract #, Center Name FY XXXX-XXXX
Name/Position of Individual Completing Report
Email Address of Individual Completing Report
Deliverable | Month | Progress Towards Deliverable (#) | Narrative
Quarterly Reporting
C.1.6.3 The Provider shall ensure the BAS participates in the CPI Project’s Quarterly Leadership Meetings to enhance batterer accountability, promote community investment, and ensure the effectiveness of the BAS Project. The Provider shall engage system leaders and leaders from underserved communities that support batterer accountability measures within the Provider's service area to attend the CPI Project’s Quarterly Leadership Meetings. The Provider’s BAS shall coordinate with the CPI Project’s DV Advocates to maintain a roster of committee members, including their roles. Narrative must include date of meeting, barriers discusses, action items to address barrieres, and local agencies/leaders the BAS invited to attend, even if they didn't attend the meeting that quarter. Include documentation of meeting in alignment with section C.2.5.4 of the contract. -C.2.5.4.2. Meeting agenda with date and time. -C.2.5.4.3. Titled sign-in sheet of attendees with printed names, original signatures, and title/position for in person trainings or meetings. -C.2.5.4.4. Official attendee roll hosted on an online platform, screenshot of live meeting or training showing attendee names. | Q1
July
August
September
Q2
October
November
December
Q3
January
February
March
Q4
April
May
June
| Annual Total | 0
C.1.2 The BAS shall train child welfare professionals and related community partners on topics including, but not limited to, perpetrator engagement, batterer dynamics, and case plans actions that increase batterer accountability. Narrative shall include date of training, training title, and audience. Include documentation of training in alignment with section C.2.5.4 of the contract. -C.2.5.4.1. Training agenda to include course titles, descriptions, objectives, number of hours, names of instructors, title or position, and dates of completion. -C.2.5.4.3. Titled sign-in sheet of attendees with printed names, original signatures, and title/position for in person trainings or meetings. -C.2.5.4.4. Official attendee roll hosted on an online platform, screenshot of live meeting or training showing attendee names. | Q1
July
August
September
Q2
October
November
December
Q3
January
February
March
Q4
April
May
June
| Annual Total | 0
Monthly Reporting
C.1.1 Maintain one full-time (1 FTE) Batterer Accountability Specialist (Specialist) who is co-located at either the Regional DCF, Child Welfare program office or within the court system. This position may not supervise any direct service programs or conduct any direct services for survivors of domestic violence or their children. | July
August
September
October
November
December
January
February
March
April
May
June
| Annual Total | 0
C.1.6.1 The BAS shall meet weekly with the local co-located Child Protective Investigations (CPI) Project Domestic Violence (DV) Advocate(s) to review current referrals, share information to enhance survivor safety plans and advocacy services, identify and create plans to address project implementation gaps, create and enhance training opportunities for child welfare professionals and system partners, and develop Leadership Meeting agendas that include barriers and actions items to address identified barriers. **Submit monthly summary of the topics addressed at the weekly meetings with meeting dates and staff in attendance. | July
August
September
October
November
December
January
February
March
April
May
June
| Annual Total | 0
C.1.6.2 The Provider’s programmatic and operational leadership shall attend all virtual and in-person training and technical assistance events, as required by the Department, throughout the implementation of this BAS Project, unless otherwise stipulated by the Department. | July
August
September
October
November
December
January
February
March
April
May
June
| Annual Total | 0
C.1.6.4 . The Provider shall participate in Coordinated Community Response Team (CCR), Sexual Assault Response Team (SART), or other Multidisciplinary Team (MDT) meetings. Narrative must include name and date of meeting attended. **Submit agenda and attendace log that documents the STOP funded position attended the meeting. | July
August
September
October
November
December
January
February
March
April
May
June
| Annual Total | 0
C.1.4 The BAS shall provide subject matter expertise (consultation) to child welfare professionals to guide the creation of safety actions and case plans that increase batterer accountability and compliance. **Count all consultations provided on each case during the reporting month. | July
August
September
October
November
December
January
February
March
April
May
June
| Annual Total | 0
Batterer referrals recommended to child welfare professional during consultations. | Referral Types |  | July | August | Sept | October | November | December | January | February | March | April | May | June | Annual Total
| Hope Florida | [13 empty] | 0
| Batterers Intervention Programs | [13 empty] | 0
| Fatherhood Initiative Programs | [13 empty] | 0
| Parenting Classes | [13 empty] | 0
| Inidividual Counseling | [13 empty] | 0
| Job Readiness/Placement | [13 empty] | 0
| Substance Use Programs | [13 empty] | 0
| Other (number of referrals) | [13 empty] | 0
| Other (referral types narrative) | [13 empty] | 0
| Monthly Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C.1.3 The BAS shall attend dependency case staffings and court hearings identified by the Department’s Child and Family Well-Being Regional Program Office involving cases with “Intimate Partner Violence Threatens Child” / “Household Violence Threatens Child” or other maltreatments that also involve intimate partner violence. | July
August
September
October
November
December
January
February
March
April
May
June
| Annual Total | 0 | bar: July
Performance Measure
E.1.1 The Provider shall monitor a minimum of 90% of the cases the BAS is consulted on by child welfare professionals for batterers’ compliance with dependency case plans and other court orders. | Number of child welfare cases BAS provided consultation (New cases this month) | Number of child welfare cases BAS initiatied monitoring batterer compliance | July: % of Compliance
July | 0 | 0 | July: #DIV/0!
August | 0 | 0 | July: #DIV/0!
September | 0 | 0 | July: #DIV/0!
October | 0 | 0 | July: #DIV/0!
November | 0 | 0 | July: #DIV/0!
December | 0 | 0 | July: #DIV/0!
January | 0 | 0 | July: #DIV/0!
February | 0 | 0 | July: #DIV/0!
March | 0 | 0 | July: #DIV/0!
April | 0 | 0 | July: #DIV/0!
May | 0 | 0 | July: #DIV/0!
June | 0 | 0 | July: #DIV/0!
Annual Total | 0 | 0 | July: #DIV/0!
E.1.2. The Provider’s BAS shall provide consultations to child welfare professionals that guide the creation of safety actions and case plans that increase batterer accountability to enhance survivor and child safety in 90% of total consultations. | Number of child welfare cases BAS provided consultation (New cases this month) | Number of child welfare cases that guided creation of safety actions and case plans that increase batterer accountability | July: % of Compliance
July | 0 | 0 | July: #DIV/0!
August | 0 | 0 | July: #DIV/0!
September | 0 | 0 | July: #DIV/0!
October | 0 | 0 | July: #DIV/0!
November | 0 | 0 | July: #DIV/0!
December | 0 | 0 | July: #DIV/0!
January | 0 | 0 | July: #DIV/0!
February | 0 | 0 | July: #DIV/0!
March | 0 | 0 | July: #DIV/0!
April | 0 | 0 | July: #DIV/0!
May | 0 | 0 | July: #DIV/0!
June | 0 | 0 | July: #DIV/0!
Annual Total | 0 | 0 | July: #DIV/0!
Revised April 2026
For Official Use ONLY - Do not edit
DCF
CBC
Yes
No
N/A
Previously Documented

## Example Report
BAS Template 1 - STOP Monthly Report
LN111 Disney World Corp FY 2025-2026
Name/Position of Individual Completing Report | Mickey Mouse, BAS
Email Address of Individual Completing Report | mickey.mouse@disney.net
Deliverable | Month | Progress Towards Deliverable (#) | Narrative
Quarterly Reporting
C.1.6.3 The Provider shall ensure the BAS participates in the CPI Project’s Quarterly Leadership Meetings to enhance batterer accountability, promote community investment, and ensure the effectiveness of the BAS Project. The Provider shall engage system leaders and leaders from underserved communities that support batterer accountability measures within the Provider's service area to attend the CPI Project’s Quarterly Leadership Meetings. The Provider’s BAS shall coordinate with the CPI Project’s DV Advocates to maintain a roster of committee members, including their roles. Narrative must include date of meeting, barriers discusses, action items to address barrieres, and local agencies/leaders the BAS invited to attend, even if they didn't attend the meeting that quarter. Include documentation of meeting in alignment with section C.2.5.4 of the contract. -C.2.5.4.2. Meeting agenda with date and time. -C.2.5.4.3. Titled sign-in sheet of attendees with printed names, original signatures, and title/position for in person trainings or meetings. -C.2.5.4.4. Official attendee roll hosted on an online platform, screenshot of live meeting or training showing attendee names. | Q1
| July | 1 | 7/25/25 - Walt Disney Corp announced new grant award for BAS to support system. Job positing was shared.
| August | 0 | No QLM.
| September | 0 | No QLM.
Q2
| October | 1 | 10/25/25 - BAS introduced to leadership team; overview of BAS role; determined communication protocol between BAS and child welfare professionals. Invited two BIP providers to attend meetings.
| November | 0 | No QLM.
| December | 0 | No QLM.
Q3
| January | 1 | 1/25/26 - BAS shared project data; barrier identified by BAS is need for increased connectivity to CBC for batterer monitoring during case plans; CBC leadership suggested BAS provide training to CMs on their role at next all staff meeting. Invited ChildNet's Case Managment Program Leadership to attend meeting.
| February | 0 | No QLM.
| March | 0 | No QLM.
Q4
| April | 1 | 4/25/26 BAS share project data; noted increase in connectivity with CBC since training conducted; BAS identified gap in accessing information about batterers in criminal court system; Disney World Corp scheduling a meeting with SAO to determine what information can be accessed and how. Invited State Attorney's Office to attend meeting.
| May | 0 | No QLM.
| June | 0 | No QLM.
| Annual Total | 4
C.1.2 The BAS shall train child welfare professionals and related community partners on topics including, but not limited to, perpetrator engagement, batterer dynamics, and case plans actions that increase batterer accountability. Narrative shall include date of training, training title, and audience. Include documentation of training in alignment with section C.2.5.4 of the contract. -C.2.5.4.1. Training agenda to include course titles, descriptions, objectives, number of hours, names of instructors, title or position, and dates of completion. -C.2.5.4.3. Titled sign-in sheet of attendees with printed names, original signatures, and title/position for in person trainings or meetings. -C.2.5.4.4. Official attendee roll hosted on an online platform, screenshot of live meeting or training showing attendee names. | Q1
| July | 0 | No training being developed or provided.
| August | 0 | Offender Accountabilty Strategies training being developed.
| September | 1 | Offender Accountabilty Strategies training presented to DCF staff on 9/26/25
Q2
| October | 0 | No training being developed or provided.
| November | 1 | Offender Accountabilty Strategies training presented to Disney World Corp staff on 11/1/25
| December | 0 | No training being developed or provided.
Q3
| January | 0 | Training on BAS role and supports to child welfare system being developed.
| February | 0 | Training on BAS role and supports scheduled for CBC in March
| March | 1 | 3/5/26 Training on BAS role and supports presented to CBC.
Q4
| April | 1 | 4/10/26 Training on BAS role and supports presented to Disney World Corp staff
| May | 0 | No training being developed or provided.
| June | 0 | No training being developed or provided.
| Annual Total | 4
Monthly Reporting
C.1.1 Maintain one full-time (1 FTE) Batterer Accountability Specialist (Specialist) who is co-located at either the Regional DCF, Child Welfare program office or within the court system. This position may not supervise any direct service programs or conduct any direct services for survivors of domestic violence or their children. | July | 0 | New contract, recruiting for position
| August | 0 | New contract, interviewed scheduled
| September | 1 | Donald Duck has filled the position since 10/10/25. Core Scheduled for November
| October | 1 | Donald Duck has filled the position since 10/10/25.
| November | 1 | Donald Duck has filled the position since 10/10/25.
| December | 1 | Donald Duck has filled the position since 10/10/25.
| January | 1 | Donald Duck has filled the position since 10/10/25.
| February | 1 | Donald Duck has filled the position since 10/10/25.
| March | 1 | Donald Duck has filled the position since 10/10/25.
| April | 0 | Position vacant 4/10/26
| May | 1 | Tinker Bell has filled the position since 5/7/25. Core scheduled for end of May.
| June | 1 | Tinker Bell has filled the position since 5/7/25
| Annual Total | 9
C.1.6.1 The BAS shall meet weekly with the local co-located Child Protective Investigations (CPI) Project Domestic Violence (DV) Advocate(s) to review current referrals, share information to enhance survivor safety plans and advocacy services, identify and create plans to address project implementation gaps, create and enhance training opportunities for child welfare professionals and system partners, and develop Leadership Meeting agendas that include barriers and actions items to address identified barriers. **Submit monthly summary of the topics addressed at the weekly meetings with meeting dates and staff in attendance. | July | 0 | position vacant
| August | 0 | position vacant
| September | 1 | BAS met weekly with DVCW Adv
| October | 1 | BAS met weekly with DVCW Adv
| November | 1 | BAS met weekly with DVCW Adv
| December | 1 | BAS met weekly with DVCW Adv
| January | 1 | BAS met weekly with DVCW Adv
| February | 1 | BAS met weekly with DVCW Adv
| March | 1 | BAS met weekly with DVCW Adv
| April | 0 | position vacant
| May | 1 | BAS met weekly with DVCW Adv
| June | 1 | BAS met weekly with DVCW Adv
| Annual Total | 9
C.1.6.2 The Provider’s programmatic and operational leadership shall attend all virtual and in-person training and technical assistance events, as required by the Department, throughout the implementation of this BAS Project, unless otherwise stipulated by the Department. | July | 0 | No project training or TA conducted.
| August | 1 | Attended FLDVC Child Welfare Initiative Call
| September | 1 | Attended FLDVC Child Welfare Initiative Call
| October | 1 | Attended FLDVC Child Welfare Learning Exchange
| November | 0 | No project training or TA conducted.
| December | 1 | Donald Duck attended Quarterly STOP Victim Services Meeting.
| January | 0 | No project training or TA conducted.
| February | 1 | Attended FLDVC Child Welfare Initiative Call
| March | 1 | Donald Duck attended Quarterly STOP Victim Services Meeting.
| April | 0 | No project training or TA conducted.
| May | 1 | Attended FLDVC Child Welfare Initiative Call
| June | 1 | Tinkerbell attended Quarterly STOP Victim Services Meeting.
| Annual Total | 8
C.1.6.4 . The Provider shall participate in Coordinated Community Response Team (CCR), Sexual Assault Response Team (SART), or other Multidisciplinary Team (MDT) meetings. Narrative must include name and date of meeting attended. **Submit agenda and attendace log that documents the STOP funded position attended the meeting. | July | 1 | Disney World Corp attended SART Meeting on 7/15/25.
| August | 1 | Disney World Corp attended DV CCR Meeting on 8/6/25.
| September | 0 | No meetings held this month.
| October | 0 | No meetings held this month.
| November | 0 | No meetings held this month.
| December | 1 | Disney World Corp attended SART Meeting on 12/15/25.
| January | 1 | Disney World Corp attended DV CCR Meeting on1/6/26.
| February | 0 | No meetings held this month.
| March | 0 | No meetings held this month.
| April | 0 | No meetings held this month.
| May | 1 | Disney World Corp attended SART Meeting on 5/15/26.
| June | 1 | Disney World Corp attended DV CCR Meeting on 6/6/26.
| Annual Total | 6
C.1.4 The BAS shall provide subject matter expertise (consultation) to child welfare professionals to guide the creation of safety actions and case plans that increase batterer accountability and compliance. **Count all consultations provided on each case during the reporting month. | July | 21 | Provided 21 consultation services.
| August | 19 | Provided 19 consultation services.
| September | 22 | Provided 22 consultation services.
| October | 10 | Provided 10 consultation services.
| November | 9 | Provided 9 consultation services.
| December | 17 | Provided 17 consultation services.
| January | 20 | Provided 20 consultation services.
| February | 24 | Provided 24 consultation services.
| March | 21 | Provided 21 consultation services.
| April | 22 | Provided 22 consultation services.
| May | 19 | Provided 19 consultation services.
| June | 23 | Provided 23 consultation services.
| Annual Total | 227
C.1.3 The BAS shall attend dependency case staffings and court hearings identified by the Department’s Child and Family Well-Being Regional Program Office involving cases with “Intimate Partner Violence Threatens Child” / “Household Violence Threatens Child” or other maltreatments that also involve intimate partner violence. | July | 10 | 5 case staffings; 5 court hearings
| August | 8 | 3 case staffings; 5 court hearings
| September | 12 | 2 case staffings; 10 court hearings
| October | 4 | 4 case staffings
| November | 7 | 5 case staffings; 2 court hearings
| December | 11 | 8 case staffings; 3 court hearings
| January | 13 | 3 case staffings; 10 court hearings
| February | 22 | 11 case staffings; 11 court hearings
| March | 24 | 21 case staffings; 3 court hearings
| April | 11 | 11 court hearings
| May | 13 | 12 case staffings; 1 court hearing
| June | 9 | 9 case staffings
| Annual Total | 144
Performance Measure
E.1.1 The Provider shall monitor a minimum of 90% of the cases the BAS is consulted on by child welfare professionals for batterers’ compliance with dependency case plans and other court orders. | Number of child welfare cases BAS provided consultation (New cases this month) | Number of child welfare cases BAS initiatied monitoring batterer compliance | % of Compliance | Performance measure data pulls directly from Template 1A each month.
July | 0 | 0 | #DIV/0!
August | 0 | 0 | #DIV/0!
September | 0 | 0 | #DIV/0!
October | 0 | 0 | #DIV/0!
November | 0 | 0 | #DIV/0!
December | 0 | 0 | #DIV/0!
January | 0 | 0 | #DIV/0!
February | 0 | 0 | #DIV/0!
March | 0 | 0 | #DIV/0!
April | 0 | 0 | #DIV/0!
May | 0 | 0 | #DIV/0!
June | 0 | 0 | #DIV/0!
Annual Total | 0 | 0 | #DIV/0!
E.1.2. The Provider’s BAS shall provide consultations to child welfare professionals that guide the creation of safety actions and case plans that increase batterer accountability to enhance survivor and child safety in 90% of total consultations. | Number of child welfare cases BAS provided consultation (New cases this month) | Number of child welfare cases that guided creation of safety actions and case plans that increase batterer accountability | % of Compliance
July | 0 | 0 | #DIV/0!
August | 0 | 0 | #DIV/0!
September | 0 | 0 | #DIV/0!
October | 0 | 0 | #DIV/0!
November | 0 | 0 | #DIV/0!
December | 0 | 0 | #DIV/0!
January | 0 | 0 | #DIV/0!
February | 0 | 0 | #DIV/0!
March | 0 | 0 | #DIV/0!
April | 0 | 0 | #DIV/0!
May | 0 | 0 | #DIV/0!
June | 0 | 0 | #DIV/0!
Annual Total | 0 | 0 | #DIV/0!

## Template 1A-July
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-August
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-September
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-October
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-November
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-December
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-January
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-February
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-March
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-April
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-May
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!

## Template 1A-June
Template 1A - Consultation Tracking Log - 10/2025
[Center Name]
DCF or CBC Case ID | Consultation with DCF or CBC | Child Welfare Case Intake Date | Date CW Requested Initial Consultation | Date of Initial Consultation (even if previous month) | Additional Consultation Dates (reporting month only) | Total # of Consultations on Case (reporting month only) | BAS monitoring batterer compliance with dependency case plans and other court orders (CBC/CMO Only) | At least one consultation included guidance on safety actions and case plans to increase batterer accountability | BAS Name | Consultation Notes Document the subject matter expertise topics provided. Example: BAS assisted CPI or DCM in identifying batterer generated risk factors, identifying and documenting batterer's patterns of coercive control, the impact of the perpetrator’s behavior and actions on children, interviewing the offender, identifying survivor’s protective capacities, and guided the child welfare professional in creating safety actions and case plans that increase batterer accountability to enhance survivor and child safety. BAS initiated batterer compliance monitoring. Narrative is a cumulative report of all topics covered during all consultations this month.
#VALUE!